## Sprint_1
Project: Tras.h2o Class: COMP8117-R-2022S Project director: Prof. Dr. Usama Mir Project_client: Ms. Saroj Dayal Sprint1 : 2022-05-20 to 2022-05-29
Name | ID | Story
Ayush Kaushik Mistry | 110087260 | Project Proposal Initiation
Harsh Bharath Nimmakuri | 110088953 | Project proposal documentation
Karan Amitkumar Zaveri | 110062029 | Project Proposal Initiation
Marc Smith | 110087601 | Project Proposal Initiation
Parth Ashokbhai Patel | 110071969 | Project Proposal Initiation
Pranjali Mukeshkumar Prajapathi | 110087663 | Project Proposal Initiation
y

## Sprint_2
Project: Tras.h2o Class: COMP8117-R-2022S Project director: Prof. Dr. Usama Mir Project_client: Ms. Saroj Dayal Sprint2 : 2022-05-30 to 2022-06-12
Name | ID | Story
Ayush Kaushik Mistry | 110087260 | Setting up the navigation; login and signup features
Harsh Bharath Nimmakuri | 110088953 | learning about react native
Karan Amitkumar Zaveri | 110062029 | learning about react native
Marc Smith | 110087601 | setting up the docker container
Parth Ashokbhai Patel | 110071969 | learning about react native
Pranjali Mukeshkumar Prajapathi | 110087663 | learning about react native

## Sprint_3
Project: Tras.h2o Class: COMP8117-R-2022S Project director: Prof. Dr. Usama Mir Project_client: Ms. Saroj Dayal Sprint3 : 2022-06-13 to 2022-06-26
Name | ID | Story
Ayush Kaushik Mistry | 110087260 | working on the API integratio nof the app
Harsh Bharath Nimmakuri | 110088953 | working on user profile design UI
Karan Amitkumar Zaveri | 110062029 | setting up the screens and templates for leaderboards
Marc Smith | 110087601 | creating django models
Parth Ashokbhai Patel | 110071969 | learning about react native
Pranjali Mukeshkumar Prajapathi | 110087663 | working on rewards UI

## Sprint_4
Project: Tras.h2o Class: COMP8117-R-2022S Project director: Prof. Dr. Usama Mir Project_client: Ms. Saroj Dayal Sprint4 : 2022-06-27 to 2022-07-10
Name | ID | Story
Ayush Kaushik Mistry | 110087260 | adding validations to the authentication screens and log data screens
Harsh Bharath Nimmakuri | 110088953 | working on the refill data collection and preparing json object
Karan Amitkumar Zaveri | 110062029 | working on the UI and logic for leaderboards
Marc Smith | 110087601 | define the urls and views
Parth Ashokbhai Patel | 110071969 | working on the admin.py and units tests for the backend
Pranjali Mukeshkumar Prajapathi | 110087663 | Working with the refill UI and navigation on maps

## Sprint_5
Project: Tras.h2o Class: COMP8117-R-2022S Project director: Prof. Dr. Usama Mir Project_client: Ms. Saroj Dayal Sprint4 : 2022-07-11 to 2022-07-24
Name | ID | Story
Ayush Kaushik Mistry | 110087260 | solving the bugs and generating the apk
Harsh Bharath Nimmakuri | 110088953 | forgot password functionality, PPT for client demo, final report documentation
Karan Amitkumar Zaveri | 110062029 | completing the report and user profile api integration
Marc Smith | 110087601 | fixing on the backend bugs, debugging
Parth Ashokbhai Patel | 110071969 | Unit test cases for the front end and bug fixes
Pranjali Mukeshkumar Prajapathi | 110087663 | completing the refill points and rewards screen

## Gantt_chart
Sprint | Task_name | Start | 2022-05-20 | [5 empty] | 2022-05-30 |  |  |  |  | 2022-06-13 |  |  |  |  | 2022-06-27 |  |  |  |  | 2022-07-11
|  |  | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
Sprint - 1 | Project Idea Initiation | 2022-05-20
| Daily Scrum Calls | 2022-05-20
Project Proposal - Documentation
| Initial SRS | 2022-05-23
| Use Case Diagram | 2022-05-24
| Project planning | 2022-05-26
| Sample Prototype | 2022-05-25
Sprint - 2 | Daily Scrum Calls | 2022-05-30
| Project Proposal submission | 2022-06-02
Front-end development initiation
| Add log in functionality | 2022-06-03
| Add sign up functionality | 2022-06-03
| API integration of the authentication feature | 2022-06-10
| created UI design for add log func | 2022-06-10
Back-end development initiation
| create django project | 2022-05-31
| creating docker container | 2022-06-01
| set-up git | 2022-06-02
| push to AWS server | 2022-06-02
Sprint - 3 | Daily Scrum Calls | 2022-06-13
Front-end development
| Add User profile functionality | 2022-06-17
| User profile UI changes | 2022-06-23
| Add Rewards functionality | 2022-06-24
| Add the About US page | 2022-06-26
Back-end development
| push to repository | 2022-06-13
| define the model - container | 2022-06-14
| define the model - refill | 2022-06-15
| Bug / error fixes | 2022-06-06
Sprint - 4 | Daily Scrum Calls | 2022-06-27
Front-end development
| add leaderboard functionality | 2022-06-30
| add Refill points functionality | 2022-07-01
| data collection of refill points | 2022-07-08
| testing of sprint-3 | 2022-07-09
Back-end development
| define urls | 2022-06-27
| define the views / endpoints | 2022-06-28
| install third party packages | 2022-06-30
| Bug / error fixes | 2022-06-28
Sprint - 5 | Daily Scrum Calls | 2022-07-11
Front-end development
| Add Report functionality | 2022-07-15
| add forgot password functionality | 2022-07-22
| bug fixes for sprint 3 / sprint 4 | 2022-07-11
| front end user acceptance testing | 2022-07-20
Back-end development
| unit tests | 2022-07-18
| input user sample data | 2022-07-21
| input refill data | 2022-07-24
| Bug / error fixes | 2022-07-22
| Final Project Report - documentation | 2022-07-23
| Final Product Testing | 2022-07-15